## Slide 1
Accelerating Public Health Hiring: A QI Pilot to Reduce Time to Hire Through Practical Tools and Manager Engagement
Ryan Jury, RN, MBA – Acting Senior Deputy Public Health Division Director, North Carolina Department of Health and Human Services
August 20, 2025

## Slide 2: Public Health Improvement
Just Do It
Engagement
Momentum
Framework
Some projects don't need extensive discussion before implementation.
Process to get teams involved and bought into the project
Data collection methods and communication of results
Using lessons learned to tackle other improvement needs

## Slide 4
"If you want to go fast, go alone; if you want to go far, go together“
-African proverb

## Slide 6: Momentum – Problem Statement
  Increase the distance that each table’s paper airplanes will fly

## Slide 7: Momentum – How are we doing?
Activity:
Each table should fold a paper airplane.
Observations? (5 Why)

## Slide 8: Momentum – Brainstorm
What potential solutions could be used to solve the problems observed?

## Slide 9: Momentum – Current State
Start with a Piece of Paper:
  Use a standard 8.5 x 11-inch sheet of paper.
Fold the Paper in Half Lengthwise:
  Fold the paper in half lengthwise (hotdog style) and then unfold it. This creates a crease down the center.
Fold the Top Corners to the Center Crease:
  Take the top right corner and fold it down to the center crease.
  Repeat with the top left corner, creating a triangle shape at the top.
Fold the Top Edges to the Center Crease:
  Take the new top right edge and fold it to the center crease.
  Repeat with the top left edge, forming a narrower triangle.
Fold the Plane in Half:
  Fold the plane in half along the original center crease, with the folds inside.
Create the Wings:
  Fold down one side to create a wing, aligning the edge with the bottom of the plane.
  Repeat on the other side to create the second wing.
Adjust the Wings:
  Make sure the wings are even and adjust them to ensure the plane is balanced.

## Slide 10: Momentum – How are we doing?
Activity:
Each table should fold a paper airplane.
Observations? (5 Why)

## Slide 11: Momentum – Brainstorm
What potential solutions could be used to solve the problems observed?

## Slide 12: Momentum – Brainstorm
Tips for Better Flights:
  Crease Firmly: Make sure all folds are crisp and firm.
  Symmetry: Ensure both sides are symmetrical for better flight performance.
  Fail Fast: Make small adjustments to improve its flight.

## Slide 13: Momentum – How are we doing?
Activity:
Each table should fold a paper airplane.
Observations? (5 Why)

## Slide 14: Implementation in Public Health Practice

## Slide 15: Project Timeline
Accenture Current State Analysis on DPH Time to Hire
Sept 2023 – Nov 2023
QI Project Team Kick Off with CDI
Identification of Possible Solutions – DPH Driver
Voting on Action Plan
Development of 3 Time to Hire Tools
April 2024 – Aug 2024
Aug 2024 – Dec 2024
Implement of Time to Hire Tools with CDI Hiring Managers
Tracking Time to Hire Data
Feedback from Hiring Managers
Nov 2023 – April 2024
Development of QI Pilot Project Proposal
Stakeholder Engagement with CDI and DMT
Referral of QI Project to Quality Improvement Council

## Slide 16: Project Deliverables
Tool 1: Recommendations for updated job descriptions
Overview document that defines process for how and when to update job descriptions.
Walks though expectations of hiring managers and shares tips/tricks
Tool 3: Bank of Interview Questions
Intro/Instructions for Hiring Managers
Bank of interview questions group by categories
Tool 2: Recommendations for pre-blocking time for candidate interviews
Defines expectations of hiring managers for when to ID interview committee members (within 2 days of job posting) and putting holds on their calendars for potential interview times
When used in Hiring Process
Step 1: # of Days from RTP to posting
Step 3: # of Days from posting closing to applicants referred
Step 4: # of Days from applicant referred to candidate selected
Step 5: # of Days from candidate selected to salary approval
Step 7: # of Day from verbal offer to offer accepted
Step 4: # of Days from applicant referred to candidate selected
Hiring Process Metric Effected
Step 1: Hiring manager Developing RTP
Step 4: # of Days from applicant referred to candidate selected
Step 4: Hiring manager conducting Interviews
Step 2: Position Posted

## Slide 17: Project Outcomes
Chart: QI Time to Hire Pilot vs Control Group – Average Number of Days from Target
| Step 1: # of days from RTP to posting (Target = 5 days) | Step 2: # of days posted (Target = 10 days) | Step 3: # of days from posting closing to applicates referred (Target = 5 days) | Step 4: # of days from applicates referred to candidate selected (Target = 30 days) | Step 5: # of days from candidate selected to salary approval (Target = 5 days) | Step 6: # of days from salary approval to verbal offer occurring (Target = 2 days) | Step 7: # of days from verbal offer occurring to offer accepted (Target = 3 days)
QI Project | 15.54 | 4.6 | 6.07 | 5.82 | 17 | 0 | 36
Control Group | 15 | 21 | 8 | 25 | 21 | 9 | 0
* Counter offer required salary changes
Cumulative Average Number of Day Over Target through Step 5
QI Pilot: 49.03 Days Control: 90 Days
Effected by Time to Hire Tools
=

## Slide 18: Deep Dive into Vacant Positions
Chart: Status of Vacant DPH Positions - Count
| Accepted | Interview and Selection | Pending Acceptance | Position Filled | Reposted | Salary Setting Central | Salary Setting Local | Screening | Verbal Offer Pending | Blank
Count of Positions | 11 | 40 | 14 | 5 | 8 | 1 | 1 | 3 | 5 | 129
Chart: Status of 129 Blank Positions - Count
| Acting Pay | In-Range - Perm | In-Range - Temp | Job Description Update | Reallocation | (blank)
Count of Positions | 1 | 3 | 2 | 1 | 10 | 112
Status of Vacant Positions

## Slide 19: Qualitative Data from Project Hiring Managers
Problem
Issues that extend hiring process
Root Cause
Hiring Managers are encountering challenges in the hiring process that extend the hiring process – and the longer it takes to fill a position, the more likely hiring managers are to experience hiring hesitancy
Outdated Hiring Manager Resource Information
Delays due to undefined processes
HMs unclear how to navigate salary negotiations and budgeting issues
HR SharePoint/NEOGOV Recruitment Guide not up-to-date
Lack of guidance on navigating reposting process when needed (no qualified candidates or rejected offer)
Limited number of/Loss of qualified candidates
Delays/Extended time to hire timeline (specifically after step 4)
Position not budgeted at or above median of salary range